## Current Financial Close
Remote Financial Close Considerations
Non-Exhaustive
# | Month-End Close Phase | Considerations | Responsible Party | Addressed?
1 | Pre-Close and Governance | Establish a virtual command center, including Accounting, FP&A, Tax, Treasury and IT to ensure cross-functional issues can be discussed and resolved in real time. Designate a PMO lead for the command center who will act as a single point of contact throughout the close process
2 | Pre-Close and Governance | Engage regional / local teams early in the process and incorporate into virtual command center structure.
3 | Pre-Close and Governance | Determine how the meeting cadence and governance structure should be amended to conduct remote month-end close status meetings.
4 | Pre-Close and Governance | Implement cross-functional meeting cadence and outline a communication process for all impacted stakeholders who are either contributors to or recipients of financial reporting. Ensure meeting notes and action items are shared.
5 | Pre-Close and Governance | Establish guidelines for decision making, escalation and resolution of critical path issues. Ensure an authority matrix is in place to clarify decision rights and process to communicate critical decisions to key stakeholders and management.
6 | Pre-Close and Governance | Document/review current month-end close calendar, including activities, owners, accounts and dependent systems.
7 | Pre-Close and Governance | Conduct a day-by-day walkthrough of how the remote month-end close process will operate.
8 | Pre-Close and Governance | Identify owners for all material accounts and ensure availability for remote close status meetings. Identify back up owners, being mindful of segregation of duty requirements and process and controls changes impacting SOX certification.
9 | Pre-Close and Governance | Give special consideration to how centralized functions (i.e. COEs, shared service centers) will be impacted by remote work in their geographic location. Consider whether back-up plans and changes in communication / ways of working approach are needed.
10 | Pre-Close and Governance | Communicate with outsource providers (BPO) and other vendors to align on expectations of timing and identify any potential resource or timeline constraints from third parties.
11 | Pre-Close and Governance | Identify critical resources / single points of failure and establish coverage / back-up plan in case of capacity constraints or illness, being mindful of segregation of duty requirements.
12 | Pre-Close and Governance | Assess degree of people/process redundancy in the Finance function around the world to compensate for illness/absence (and avoid single-point process failure).
13 | Pre-Close and Governance | Monitor employee health and absences for need to initiate back-up plans.
14 | Pre-Close and Governance | Determine which collaboration tools are available and ensure employees understand how to use.
15 | Pre-Close and Governance | Identify potential gaps in process documentation and desktop procedures. Set up centralized repository for critical close process and training documentation. Ensure all team members are able to access content remotely.
16 | Pre-Close and Governance | Assess if you run a high volume of manual processes on a monthly or quarterly basis. Identify where and how critical the manual processes are. Develop back-up plans for critical activities.
17 | Pre-Close and Governance | Identify any non-electronic data and / or paper records which are critical to the month-end close process. Establish an alternate plan if data cannot be accessed.
18 | Pre-Close and Governance | Establish plan to obtain, document and store sign-offs and approvals during remote close status meetings, considering SOX requirements.
19 | Pre-Close and Governance | Consider whether process changes are needed to replace paper-based sign-offs with digital. Identify process to store the digital documentation, taking into consideration SOX requirements.
20 | Pre-Close and Governance | Evaluate manual controls to determine which are at increased risk in a remote workforce environment. Develop mitigation plans, considering SOX requirements.
21 | Pre-Close and Governance | Assess the need to establish incremental process controls in areas significantly impacted by remote close process or change in business environment.
22 | Pre-Close and Governance | Document deviations from standard processes and controls
23 | Pre-Close and Governance | Inventory all financial systems used in the month-end close process, assess criticality, remote access and bandwidth capabilities and assess cybersecurity impact.
24 | Pre-Close and Governance | Identify systems which are not available via remote access or have highly limited access controls and determine alternate procedures.
25 | Pre-Close and Governance | Align with IT on what systems support resources will be available during the close process. Designate on-call resources during critical periods (e.g. Day 1-5).
26 | Pre-Close and Governance | Test access to all systems and third party data feeds prior to start of month-end close.
27 | Pre-Close and Governance | Test payroll process and bank releases (internally or with third party providers) prior to start of month-end close.
28 | Pre-Close and Governance | Consider how disclosure and audit committee meetings will operate in a remote environment. Pre-test any enabling technology prior to these events.
29 | Pre-Close and Governance | Perform forecasting and data analytics, update/rebuild financial models as needed to prepare cash flow projections and perform impairment testing
30 | Pre-Close and Governance | Evaluate what diagnostic tools are available for variance analysis and FP&A. Determine if additional tools or activities are required in light of the current situation.
31 | Pre-Close and Governance | Implement any critical tools & technology to enable remote financial close.
32 | Pre-Close and Governance | Coordinate with auditors for remote activities
33 | Pre-Close and Governance | Communicate with Legal, Operations, Sales and other departments that are upstream of Finance to understand how they are impacted by the current environment to determine if changes to foreccast, accounting adjustments and SOX documentation are needed.
34 | General Accounting | Identify work that can be completed before the period end, using estimates where needed (e.g. recording depreciation on fixed assets, salary accruals, etc.)
35 | General Accounting | Plan to estimate goods in transit and work in progress by communicating with Operations to understand shipments that are expected to be completed before month-end.
36 | General Accounting | Assess outstanding Accounts Receivable balances and collectability, perform predictive modeling if needed. Incorporate impact of temporary business closures and broader macroeconomic environment into calculation of judgmental AR reserves.
37 | General Accounting | Consider supply chain disruptions and impact on critical vendors. Evaluate inventory balances to identify expected slow-moving or obsolete inventory which may need to be written off.
38 | General Accounting | Evaluate materiality thresholds and risk rankings for non-key accounts. Consider deferring completion of account reconciliations for non-critical accounts to a non-quarter end.
39 | External Reporting | Examine process for manual journal entries and consider raising (and/or enforcing) the materiality threshold in an escalating fashion throughout the close (e.g. $100K on Day 1 with approval of BU Controller, $250K on Day 2 with approval of Global Controller and $500K on Day 3 - 5 with CFO approval). Adjust SOX documentation accordingly.
40 | External Reporting | Determine which estimates you make in the current process, and which can you make with reasonable accuracy, given the current business environment. Consider whether additional reviews and approvals should be required. Adjust SOX documentation accordingly.
41 | External Reporting | Identify countries within your legal entity structure that are high risk and assess ability to make reasonable estimates of month end balances using forecasts or budgets. Design workarounds, as needed, including appropriate review and approval. Adjust SOX documentation accordingly.
42 | External Reporting | Identify long-lived assets, goodwill and intangibles which may subject to an impairment analysis due to change in business conditions.
43 | External Reporting | Assess whether any changes in employee structure will require additional accruals to be recorded (e.g. layoffs, severance, etc.)
44 | External Reporting | Perform analysis/modeling of reserves amounts with management review and approval of any changes from previous quarters.
45 | External Reporting | Evaluate cost and equity method investments to determine if there has been any "other than temporary" decline in the value of an investee which would trigger impairment.
46 | External Reporting | Perform preliminary GL account level analytics to document key drivers of account fluctuations. Discuss any material movements with management early in the process.
47 | External Reporting | Assess changes in manufacturing capacity for impact on inventory costing
48 | External Reporting | With reference to annual goodwill impairment, analyze fair value of reporting units and indefinite live assets
49 | External Reporting | Start discussions early with IR, Board of Directors and other stakeholders around earnings release messaging.
50 | External Reporting | Ensure audit and other relevant board committees are provided with detailed pre-read materials and absences are planned for
51 | Taxes | Monitor international, federal and state and local legislation for impact on company's taxes, grants or incentives
52 | Taxes | Determine if there are jurisdictions projecting a loss for the year and assess whether the loss is expected to be realizable
53 | Taxes | Obtain updated forecasted income or loss for the year to determine the estimated annual effective tax rate
54 | Taxes | Review forecast for consistency with other financial accounting estimates used
55 | Taxes | If forecast is not reliable or cannot be reasonably estimated, determine if the actual ETR should be used for interim period
56 | Taxes | Determine if changes in supply chains and operations are reflected in the projected mix of pre-tax earnings
57 | Taxes | Update estimates of deferred tax assets and assess for realizability
58 | Taxes | Finance, Tax and Treasury to determine if it is apparent there is a change in assertion regarding outside basis differences in foreign subsidiaries
59 | Taxes | Consider special tax accounting rules for losses from continuing operations
60 | Taxes | Evaluate government grants or incentives on indirect taxes
61 | Taxes | Consider potential changes in estimated apportioned state tax rate
62 | Taxes | Re-estimate permanent differences for meals and entertainment expenses
63 | Taxes | Determine changes on tax accounts from interest disallowance rules
64 | Taxes | Consider additional tax disclosures for changes in estimates and management judgements
65 | SEC Filing | Evaluate which processes are in place to address incremental SEC reporting needs, including changes to regulatory requirements, revisions to earnings guidance and impact on disclosures.
66 | SEC Filing | Review published SEC guidance to understand any changes to regulatory and reporting guidelines.
67 | SEC Filing | Assess the Company's going concern due to business disruption and liquidity constraints
68 | SEC Filing | Identify need for additional disclosures as a result of changes in the business environment, including but not limited to, known trends and uncertainties within MD&A, risk factors and safe harbor disclosure regarding forward-looking statements.
69 | SEC Filing | Perform analysis/modeling of “material” risks for disclosure requirements.
70 | SEC Filing | Ensure management (including non-Finance executives) are sufficiently prepared to sign-off on incremental disclosures and complete 302 certifications on accelerated timeline. Consider implementing an additional layer of sub-certifications to the review process.
71 | SEC Filing | Evaluate how the public health crisis is expected to impact the business forecast in the remainder of the fiscal year. Consider whether recent developments necessitate the Company issuing a revision to previously released earnings guidance.
72 | SEC Filing | Anticipate questions which will be raised by executives, Board of Directors, analysts and investors. Compile a robust Q&A document to ensure that the executive and investor relations teams are sufficiently prepared to communicate during the earnings press release and conference call.

## Prepare for Future Cycles
Remote Financial Close Considerations
Non-Exhaustive
# | Month-End Close Phase | Considerations | Responsible Party | Addressed?
1 | Prepare for Future Cycles | Conduct robust close debrief to determine improvements needed for future period-end close cycles.
2 | Prepare for Future Cycles | Implement tools & technology to streamline financial close process (e.g. enhanced usage of workflow and collaboration tools, quick automation opportunities).
3 | Prepare for Future Cycles | Consider implementing longer-term efficiencies for future periods, including chart of account simplification, auto-reconciliation capabilities and close process project management / workflows tools.
4 | Prepare for Future Cycles | For future cycles, consider which tasks or activities can be shifted prior to month end. For example, establishing cut-off for final payment run one week prior to close.
5 | Prepare for Future Cycles | Consider simplifying allocation and reclass activities to improve efficiency.
6 | Prepare for Future Cycles | Designate process owners to drive efficiency, both within Finance as well as other functions such as Legal, Procurement, HR, IT, etc. If Global Process Owners are not already identified, consider doing so now.
7 | Prepare for Future Cycles | Evaluate ongoing data and information needs for accounting and disclosure and develop processes to obtain on a timely basis.
8 | Prepare for Future Cycles | Evaluate readiness for Digital Audit and SOX testing
9 | Prepare for Future Cycles | Develop remote internal audit and internal controls approach